ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Municipality of Debrca

## Country background

Republic of North Macedonia is a candidate country for membership expecting commencement of membership negotiations. The next phase in the accession process is acquiring negotiation date for European Union membership.

The negotiation process of the Republic of North Macedonia for EU membership will signify completion of the approximation process to the European Union, adoption of its benefits and values as well as complete adaptation of the Macedonian institutions towards functioning to that of the Union institutions. The negotiations will also signify establishing grounds and preparation for a successful functioning of the Republic of North Macedonia as a Union Member State. In February 2008, the Council of Ministers of the European Union adopted the 2008 Accession Partnership of the Republic of Macedonia. The negotiations as a comprehensive dynamic undertaking, require full preparation of the state authorities and institutions as well as of the structures established for coordination and conducting negotiations prior to the commencement of the negotiations themselves.

## Current situation in the sector

The wider area of Belchisko Swamp is 460 hectares and the wetland areas are approx. 50 hectares, while the total area of the Municipality of Debrca is approximately 42.500 hectares.

## The area of Belchisko Swamp is unique for the country and it is proposed to be declared protected area under category of a monument of nature. It is also part of the European EMERALD network that comprises areas with particular interest for protection and it will be probably a part of the NATURA 2000. Related programmes and other donor activities

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

## The overall objective of the project is the protection and conservation of threatened and indigenous species of flora in the cross border area. It is directly related to the specific objective 2.3 of the programme "sustainable management of protected areas, ecosystems and biodiversity.

Other specific objectives of the project are:

1. To set the priorities for the most endangered flora of the cross border area, setting the Prioritized Plants (PP).

2. To develop a concrete joint cross border strategy for the documentation of the prioritized flora species,

3. To connect scientific and protection bodies of the cross broader area setting common targets for the protection of flora biodiversity,

4. To create original scientific work that will contribute to the further study of the local flora,

5. To develop the necessary infrastructure for the sustainability of the results,

6. To involve the local authorities as a force to be reckoned with in the field of the protection of the biodiversity thanks to their local character,

7. To contribute to the spread of the necessity of the protection by new innovative means.

## Purpose

The purpose of this contract is assistance in the organization of events for the Municipality of Debrca identified as activities within the CONSE PP project. The following events should be organized:

Progress management meetings – Two progress meetings should be organized. For each meeting around 10 participants are foreseen. The organization of the meeting include venue, translator/interpreter, preparation of working material, refreshment and luch. Each meeting will take two days.

Final event-Organization of final event with 100 participants. The organization includes venue, renting audio and media equipment, preparation of working materials, translation, moderation for two days, refreshments and lunch.

Training of local guides-three days long training will require venue, renting of equipment, refreshments.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear understanding of the contract objectives and purposes on behalf of the Contractor;

- Timely information for the respective place and date of the events provided by the Contracting Authority;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation.

## Risks

Potential risks to the successful implementation of the contract include:

- Lack of communication and logistical coordination between the Contractor and the Contracting Authority. In order to avoid this risk, the Contractor should be proactive and maintain continuous contact with the relevant representatives of the Contracting Authority.

- Insufficient quality of the services provided by the Contractor. In order to avoid this risk the Contractor should use the most reliable and experienced staff/service providers on its disposal.

# SCOPE OF THE WORK

## General

### Description of the assignment

The assignment includes all necessary services that the Contractor shall carry out for the overall logistical coordination and the organization of the events mentioned in p. 2.2. Each event has to be organized separately, at different dates. For each event the Contractor will have to provide a variety of professional services, such as: accommodation arrangements for the relevant participants, rent of hall/equipment for the events and catering for participants.

The exact dates of the listed below events will be determined by the Contracting authority in due time before the respective event in order for the Contractor to be able to ensure accommodation, catering and other related services.

### Geographical area to be covered

Geographical area to be covered is the eligible area of the programme Interreg-IPA CBC Greece – Republic of North Macedonia 2014-2020

### Target groups

Representatives of project beneficiaries from both countries, as well as local guides from the Municipality of Debrca.

## Specific work

For the implementation of the activities, the following services need to be ensure

Progress meetings – 2 meetings. The specification below is per meeting.

Provisional period for implementation of first meeting: 5-6 March 2020

Location: Ohrid, North Macedonia

Number of participants: 20

CONFERENCE HALL

- A conference hall or a meeting room, ensuring enough space for 20 seated participants;

TECHNICAL EQUIPMENT

- computer connected with the multimedia in order to be ready to load the PowerPoint presentations for the event

- multimedia projector

- professional conference audio-sound system

- Translator

- flip chart with paper and markers

The equipment should be rented for 1 day and a half.

CATERING

The catering should be provided for 20 people and it should include:

- 2 cups of coffee and tea per person;

- 1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml) per person;

- At least 3 serving pieces of warm cocktail snacks per person;

- At least 3 serving pieces of cold cocktail snacks per person;

- At least 2 pieces of cocktail deserts;

- Light lunch for 20 people for each of the days

The tables where the catering will be situated should be arranged by the Contractor. There should be also provided cups, sugar, creamer, stirrer, napkins, and dishes. There should be also provided cocktail tables to be used by the participants for the coffee break. The Contractor will receive agenda of the press-conference with specified hours for the coffee-break, according to which they should ensure the arrangement of the catering.

Final meeting. The specification below is per meeting.

Provisional period for implementation of first meeting: Not determined yet

Location: Ohrid, North Macedonia

Number of participants: 20

CONFERENCE HALL

- A conference hall or a meeting room, ensuring enough space for 100 seated participants;

TECHNICAL EQUIPMENT

- computer connected with the multimedia in order to be ready to load the PowerPoint presentations for the event

- multimedia projector

- professional conference audio-sound system

- Translator

- Moderator

- flip chart with paper and markers

The equipment should be rented for 1 day.

CATERING

The catering should be provided for 100 people and it should include:

- 2 cups of coffee and tea per person;

- 1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml) per person;

- At least 3 serving pieces of warm cocktail snacks per person;

- At least 3 serving pieces of cold cocktail snacks per person;

- At least 2 pieces of cocktail deserts;

- Light lunch for 100 people for each of the days

The tables where the catering will be situated should be arranged by the Contractor. There should be also provided cups, sugar, creamer, stirrer, napkins, and dishes. There should be also provided cocktail tables to be used by the participants for the coffee break. The Contractor will receive agenda of the press-conference with specified hours for the coffee-break, according to which they should ensure the arrangement of the catering.

Training of local guides. The specification below is per meeting.

Provisional period for implementation of first meeting: Not determined yet.

Location: Ohrid, North Macedonia

Number of participants: 10

CONFERENCE HALL

- A conference hall or a meeting room, ensuring enough space for 10 seated participants;

TECHNICAL EQUIPMENT

- computer connected with the multimedia in order to be ready to load the PowerPoint presentations for the event

- multimedia projector

- flip chart with paper and markers

The equipment should be rented for 3 days

CATERING

The catering should be provided for 10 people and it should include:

- 1 cup of coffee and tea per person;

- 1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml) per person;

The tables where the catering will be situated should be arranged by the Contractor. There should be also provided cups, sugar, creamer, stirrer, napkins, and dishes. There should be also provided cocktail tables to be used by the participants for the coffee break. The Contractor will receive agenda of the press-conference with specified hours for the coffee-break, according to which they should ensure the arrangement of the catering.

## Project management

### Responsible body

Municipality of Debrca

### Management structure

The Contracting Authority is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during this contract implementation and the project as a whole.

The Contractor is fully responsible for the quality and timely delivery of the contract results, according to the contractual provisions. In this respect, the Contractor shall ensure that the reports are delivered on time and the executed activities are in line with the current Terms of Reference and the regulatory framework requirements

### Facilities to be provided by the contracting authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The operational office of the project is set up at the premises of Municipality of Debrca, s. Belchista 6344, North Macedonia

## Start date & period of implementation of tasks

The intended start date is 4 March 2020 and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for the expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that expert/s are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in Macedonian language in one original copy:

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is five days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the activities. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

2 progress meetings, 1 final event and 1 training

## Special requirements

N/A.